## App-Burndown
[11 empty] | Burndown | [11 empty] | as of | DATUM
[7 empty] | August |  |  |  |  | September |  |  |  | October |  |  |  | November
|  | Total Duration in weeks | 18 |  | Week | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  | Total Points | 105 |  | Plan | 105 | 99.1667 | 93.3333 | 87.5 | 81.6667 | 75.8333 | 70 | 64.1667 | 58.3333 | 52.5 | 46.6667 | 40.8333 | 35 | 29.1667 | 23.3333 | 17.5 | 11.6667 | 5.8333 | 2.6645e-14
|  | Points / Week planned | 5.8333 |  | Reality | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
4 | Epics |  |  |  | PpW |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 100% | EPIC 1 weights > | 25 |  | completed
| 20% | User-Requirements |  | 5 | 0% | bar: August 1 to August 2
| 25% | Rough Specification |  | 6.25 | 0% | bar: August 3 to August 4
| 15% | Detailled Specification & UI |  | 3.75 | 0% | bar: August 5
| 25% | Development |  | 6.25 | 0% | bar: September 6 to September 7
| 15% | Test & Documentation |  | 3.75 | 0% | bar: September 8
1 | 100% | EPIC 2 weights > | 35
| 15% | User-Requirements |  | 5.25 | 0% | bar: August 4
| 15% | Rough Specification |  | 5.25 | 0% | bar: August 5 to September 6
| 15% | Detailled Specification & UI |  | 5.25 | 0% | bar: September 7 to September 8
| 40% | Development |  | 14 | 0% | bar: September 9 to October 11
| 15% | Test & Documentation |  | 5.25 | 0% | bar: October 12 to October 13
1 | 100% | EPIC 3 weights > | 25
| 25% | User-Requirements |  | 6.25 | 0% | bar: September 6 to September 7
| 15% | Rough Specification |  | 3.75 | 0% | bar: September 8
| 15% | Detailled Specification & UI |  | 3.75 | 0% | bar: September 9 to October 11
| 30% | Development |  | 7.5 | 0% | bar: October 12 to October 13
| 15% | Test & Documentation |  | 3.75 | 0% | bar: November 14
1 | 100% | EPIC 4 weights > | 20
| 25% | User-Requirements |  | 5 | 0% | bar: September 8 to September 9
| 15% | Rough Specification |  | 3 | 0% | bar: October 10 to October 11
| 15% | Detailled Specification & UI |  | 3 | 0% | bar: October 12 to November 14
| 30% | Development |  | 6 | 0% | bar: November 15 to November 16
| 15% | Test & Documentation |  | 3 | 0% | bar: November 17 to November 18